## Sheet1
Smarter Health
Tech stack : Java/ReactJs
Estimation
Version 18/10/2021
TASK |  | Man Days
| Note | Backend | Frontend
PHASE 1 - SETUP
Set Up Project | Study the requirement | 0.5 | 0.5
| Initialize the source code | 0.5 | 0.5
| Design and set up DB | 3 | 0
PHASE 2 - DEVELOPMENT
Doctor's Portal
Landing Page for Doctors |  |  | 0.5
Doctors can fill in personal information manually to create the profile | - First Name - Last Name - ID Documents & Info - Contact Number (Phone Number) - Mailling Address - Email Address - DoB - Gender Validate if user is already existing upon moving forward | 1.5 | 1.5
Doctors can retrieve their personal info online | Assumption: - Doctor fill in some info - Retreive data from API | 3 | 1
Doctors can fill in professional information manually | - Qualifications - First registration & date - Current registration & date - MCR - Practising Cert Start and End Date - Specialty & Entry Date - Sub Spec & Entry Date - Family Physician status & Entry Date - Primary Practice Place - SP/GP - Designated Workplace Doctor *Assuming each piece of professional info will require a supporting document *Qualifications will be a list of items + supporting docs | 8 | 7
Doctors can save as draft and resume to view their application later | - Saving draft will link this "draft application" to an email - The doctor will receive an email with a unique URL to resume this draft | 2 | 2
Doctors can make amendment to applications after getting replies from the Management team | - Can always make amendment and resubmit - Management team will always see the status (was it a reject, or a request for amendment) | 1.5 | 1
Doctors can register a password after the application is approved | - Follow a URL on email to be directed to this view | 0.5 | 1
Doctors can login and view their complete full profile after the registration is approved | - Log the user out upon closing the browser | 1.5 | 1
Smarter Health Management
Management team can login into the management system |  | 0.5 | 1
Manage management users ( Listing, Create, Update, Delete, Disable ) | Allow the master account to create other management accounts | 2 | 2
Management team can view details of the applications |  | 2 | 3
Management team can reject an application and give reason | Input the comments Send notification via email | 1 | 1
Management team can request amendment on an application | Input the comments Send notification via email | 0.5 | 0.5
Management team can approve | On approval, send email notificaiton and allow the doctor to register with a password | 0.5 | 0.5
Management team can manage the list of doctors registered successfully (with filters on email/name included) |  | 1.5 | 1.5
Management team can view details of the doctors registered |  | 0.5 | 1
| Total Development (with buffer) | 39 | 33.8
| Timeline (estimated) | 7-8 weeks
Notes: | The items in yellow are additional features recommended in order to improve user's experience
This estimation does not include the features related to automatically retreive data from another system The items in green are just a rough estimation how long it would normally take, it is purely based on assumption

## Remaining tasks
TASK |  | Man Days
| Note | Backend | Frontend | Description | Note | Backend | Frontend
PHASE 1 - SETUP
Set Up Project | Study the requirement | 0.5 | 0.5
| Initialize the source code | 0.5 | 0.5
| Design and set up DB | 3 | 0
PHASE 2 - DEVELOPMENT
Doctor's Portal
Landing Page for Doctors |  |  | 0.5 | Update UI | Integrate authentication |  | 1
Doctors can fill in personal information manually to create the profile | - First Name - Last Name - ID Documents & Info - Contact Number (Phone Number) - Mailling Address - Email Address - DoB - Gender Validate if user is already existing upon moving forward | 1.5 | 1.5 | Update UI |  |  | 1
Doctors can fill in professional information manually | - Qualifications - First registration & date - Current registration & date - MCR - Practising Cert Start and End Date - Specialty & Entry Date - Sub Spec & Entry Date - Family Physician status & Entry Date - Primary Practice Place - SP/GP - Designated Workplace Doctor *Assuming each piece of professional info will require a supporting document *Qualifications will be a list of items + supporting docs | 8 | 7 | Update UI |  |  | 1
Doctors can register a password after the application is approved | - Follow a URL on email to be directed to this view | 0.5 | 1 | To Do
Doctors can login and view their complete full profile after the registration is approved | - Log the user out upon closing the browser | 1.5 | 1 | To Do |  | 3 | 6
Smarter Health Management
Management team can login into the management system |  | 0.5 | 1
Manage management users ( Listing, Create, Update, Delete, Disable ) | Allow the master account to create other management accounts | 2 | 2
Management team can view details of the applications |  | 2 | 3
Management team can reject an application and give reason | Input the comments Send notification via email | 1 | 1
Management team can request amendment on an application | Input the comments Send notification via email | 0.5 | 0.5
Management team can approve | On approval, send email notificaiton and allow the doctor to register with a password | 0.5 | 0.5
Management team can manage the list of doctors registered successfully (with filters on email/name included) |  | 1.5 | 1.5
Management team can view details of the doctors registered |  | 0.5 | 1